## Slide 1
Enterprise Cloud Migration & Security Program
A 14-month enterprise transformation to migrate 38 business applications from aging on-premises infrastructure to a secure AWS/Azure operating model while strengthening identity, monitoring, resilience, compliance, and cloud governance.
Budget: $4,800,000 | Duration: 14 months | Workstreams: 6 | Stakeholders: 124

## Slide 2
Strategic Outcomes
Migrate 38 applications using discovery, remediation, pilot, wave migration, validation, and decommissioning stages.
Reduce annual infrastructure run cost by at least 20% while maintaining service availability above 99.9%.
Implement centralized IAM, MFA, least-privilege access, security logging, vulnerability remediation, and cloud policy guardrails.
Establish an executive governance model with weekly delivery reviews, monthly steering committees, decision rights, and formal escalation paths.
Complete knowledge transfer, operational readiness, and legacy decommissioning without a Severity 1 migration-caused outage.

## Slide 3
Integrated Workstreams
Application Discovery & Rationalization
Cloud Foundation & Networking
Identity & Security
Migration Factory
Testing & Cutover
Operations & Change Enablement

## Slide 4
Executive KPI Results
Applications migrated: 38 → 38 (100%)
Critical security findings remediated: 47 → 45 (95.7%)
Milestones delivered on time: 32 → 31 (96.9%)
Cloud policy coverage: 100 → 98 (98%)
Training completion: 100 → 96 (96%)
Annual run-cost reduction: 20 → 21.4 (21.4%)

## Slide 5
Financial & Benefits View
Approved budget: $4,800,000
Forecast annualized benefits: $2,230,000
Infrastructure run-cost reduction: $1,090,000
Data center exit / avoided renewal: $620,000
Reduced outage/productivity loss: $315,000
Security tooling consolidation: $205,000

## Slide 6
Top Risks & Responses
R-001 — Legacy application incompatibility | High/High | Application remediation sprint and containerization assessment | Mitigated
R-002 — Identity federation delays | Medium/High | Prioritize SSO integration and establish break-glass access | Closed
R-003 — Migration wave resource contention | High/Medium | Capacity plan with protected migration windows and backup engineers | Monitoring
R-004 — Unexpected cloud spend | Medium/Medium | FinOps budgets, tagging policy, rightsizing reviews and reserved capacity analysis | Mitigated
R-005 — Business cutover resistance | Medium/Medium | Change champions, rehearsals, role-based communications and hypercare | Closed

## Slide 7
Governance & Decisions
Weekly integrated delivery review across all workstreams.
Monthly steering committee for funding, scope, timeline and risk decisions.
Formal change control for baseline impacts.
30/60/90-day benefits validation after transition.

## Slide 8
Closure & Transition
Delivery scope completed and transitioned to accountable BAU owners.
Residual risks accepted with owners and monitoring dates.
Benefits measurement transferred to business owners and Finance.
Lessons learned retained for future enterprise programs.