## Slide 1
Customer Experience Optimization Program
A 10-month cross-functional program redesigning customer support journeys, digital self-service, voice-of-customer analytics, agent workflows, and service governance across web, contact center, and operations.
Budget: $2,100,000 | Duration: 10 months | Workstreams: 5 | Stakeholders: 86

## Slide 2
Strategic Outcomes
Increase NPS by at least 10 points and CSAT to 90% or better.
Reduce average time-to-resolution by 25% and repeat contacts by 15%.
Launch a governed Voice of Customer process linking feedback themes to funded improvement initiatives.
Improve digital self-service containment while preserving escalation paths for complex issues.
Establish a single executive CX scorecard with accountable owners and monthly corrective actions.

## Slide 3
Integrated Workstreams
Voice of Customer
Digital Self-Service
Contact Center Process
CRM & Knowledge
Change, Training & Measurement

## Slide 4
Executive KPI Results
NPS: 41 → 54 (+13 pts)
CSAT: 82 → 91 (+9 pts)
First contact resolution: 68 → 79 (+11 pts)
Avg. resolution hours: 31 → 22 (-29%)
Repeat contact rate: 24 → 19 (-21%)
Self-service containment: 34 → 49 (+15 pts)

## Slide 5
Financial & Benefits View
Approved budget: $2,100,000
Forecast annualized benefits: $1,802,000
Retention uplift: $840,000
Reduced support handling cost: $465,000
Digital containment savings: $292,000
Productivity / rework reduction: $205,000

## Slide 6
Top Risks & Responses
R-001 — VOC data fragmented across channels | High/Medium | Common taxonomy, data dictionary, and weekly quality checks | Mitigated
R-002 — Agent adoption of new workflows | Medium/High | Pilot cohort, floor support, coaching and adoption dashboard | Closed
R-003 — Self-service creates dead-end journeys | Medium/High | Human escalation criteria and journey usability testing | Monitoring
R-004 — CRM configuration backlog | High/Medium | Dedicated sprint capacity and priority governance | Mitigated
R-005 — Metric definitions disputed | Medium/Medium | KPI charter with approved formulas, sources and owners | Closed

## Slide 7
Governance & Decisions
Weekly integrated delivery review across all workstreams.
Monthly steering committee for funding, scope, timeline and risk decisions.
Formal change control for baseline impacts.
30/60/90-day benefits validation after transition.

## Slide 8
Closure & Transition
Delivery scope completed and transitioned to accountable BAU owners.
Residual risks accepted with owners and monitoring dates.
Benefits measurement transferred to business owners and Finance.
Lessons learned retained for future enterprise programs.