## Slide 1
Healthcare Claims Modernization Program
A 16-month modernization program replacing fragmented claims workflows with an integrated processing, rules, reporting, and provider-support model while protecting PHI, strengthening controls, and improving adjudication performance.
Budget: $6,300,000 | Duration: 16 months | Workstreams: 6 | Stakeholders: 142

## Slide 2
Strategic Outcomes
Improve clean-claim adjudication and reduce avoidable manual touches.
Reduce average claims cycle time while maintaining payment accuracy and auditability.
Modernize integrations, rules management, reporting, and provider exception handling.
Embed privacy, access, audit, retention, and regulatory controls throughout delivery.
Execute phased cutover with reconciliation, rollback readiness, and post-launch hypercare.

## Slide 3
Integrated Workstreams
Claims Platform
Rules & Configuration
Data & Integration
Compliance & Controls
Provider Operations
Testing, Cutover & Hypercare

## Slide 4
Executive KPI Results
Clean claim rate: 83 → 94 (+11 pts)
Avg. adjudication days: 6.8 → 3.9 (-43%)
Payment accuracy: 97.2 → 99.3 (99.3%)
Manual touch rate: 29 → 17 (-41%)
Critical defects at go-live: 12 → 1 (92% reduction)
Provider inquiry volume: 100 → 78 (-22%)

## Slide 5
Financial & Benefits View
Approved budget: $6,300,000
Forecast annualized benefits: $2,585,000
Claims operations productivity: $1,260,000
Reduced rework / adjustments: $590,000
Platform maintenance reduction: $425,000
Provider service efficiency: $310,000

## Slide 6
Top Risks & Responses
R-001 — Claims rule conversion defects | High/High | Dual-run validation, rule traceability and SME signoff | Mitigated
R-002 — PHI access misconfiguration | Medium/High | Role-based access testing, audit logging and privacy review | Closed
R-003 — Interface reconciliation variance | High/High | Automated control totals and daily reconciliation | Monitoring
R-004 — Provider disruption during cutover | Medium/High | Provider communications, command center and fallback routing | Mitigated
R-005 — Regulatory reporting regression | Medium/High | Parallel reporting and compliance acceptance criteria | Closed

## Slide 7
Governance & Decisions
Weekly integrated delivery review across all workstreams.
Monthly steering committee for funding, scope, timeline and risk decisions.
Formal change control for baseline impacts.
30/60/90-day benefits validation after transition.

## Slide 8
Closure & Transition
Delivery scope completed and transitioned to accountable BAU owners.
Residual risks accepted with owners and monitoring dates.
Benefits measurement transferred to business owners and Finance.
Lessons learned retained for future enterprise programs.