## Sheet
Type | Description | Impact | Mitigation | Owner | Status
Risk | Cloud vendor delay | High | Dual-vendor strategy | PgM | Mitigated
Issue | Data migration errors | Medium | Validation scripts | Tech Lead | Closed
Dependency | Vendor API readiness | High | Weekly syncs | Vendor | Tracked